## ProjectSchedule
Quản lý thư viện
Môn học : Công nghệ phần mềm |  | Project Start: | 2020-10-09
|  | Today: | 2020-12-05
|  | Display Week: | 1 |  | 2020-10-05 | [6 empty] | 2020-10-12 | [6 empty] | 2020-10-19 | [6 empty] | 2020-10-26 | [6 empty] | 2020-11-02 | [6 empty] | 2020-11-09 | [6 empty] | 2020-11-16 | [6 empty] | 2020-11-23 | [6 empty] | 2020-11-30
 | time axis 2020-10-05 to 2020-12-06
TASK | ASSIGNED TO |  | START | END | time axis 2020-10-05 to 2020-12-06
Task 1 |  |  | 2020-10-09 | 2020-10-09
Task 2 |  |  | 2020-10-09 | 2020-10-10
Task 3 |  |  | 2020-12-04 | 2020-12-05
Task 4 |  |  | 2020-12-04 | 2020-12-05
Task 5 |  |  | 2020-12-04 | 2020-12-05
Task 6 |  |  | 2020-12-04 | 2020-12-05
Task 7 |  |  | 2020-12-04 | 2020-12-05
Task 8 |  |  | 2020-12-04 | 2020-12-05
Task 9 |  |  | 2020-12-04 | 2020-12-05
Task 10 |  |  | 2020-12-04 | 2020-12-05
Task 11 |  |  | 2020-12-04 | 2020-12-05
Task 12 |  |  | 2020-12-04 | 2020-12-05
Task 13 |  |  | 2020-12-04 | 2020-12-05
Task 14 |  |  | 2020-12-04 | 2020-12-05
Task 15 |  |  | 2020-12-04 | 2020-12-05
Task | Nội dung |  |  |  | 2020-10-05: Thành viên
Task 1 | Tạo respository trên Github |  |  |  | 2020-10-05: Huỳnh Hoàng Huy
Task 2 | Vẽ Activity Bar Chart |  |  |  | 2020-10-05: Mai Phước Thịnh
Task 3 | Tạo database |  |  |  | 2020-10-05: Nguyễn Quốc Tuấn
Task 4 | Viết class connect database |  |  |  | 2020-10-05: Vũ Ngọc Minh
Task 5 | Vẽ demo giao diện GUI |  |  |  | 2020-10-05: Huỳnh Hoàng Huy
Task 6 | Form Quản lý nhập hàng |  |  |  | 2020-10-05: Vũ Thị Hồng Xương
Task 7 | Form Thêm, sửa, xóa nhân viên,tìm kiếm |  |  |  | 2020-10-05: Mai Phước Thịnh
Task 8 | Form Thêm, sửa, xóa,tìm kiếm đọc giả |  |  |  | 2020-10-05: Vũ Ngọc Minh
Task 9 | Form Thêm, sửa, xóa,tìm kiếm sách |  |  |  | 2020-10-05: Nguyễn Minh Thiện
Task 10 | Form đăng nhập |  |  |  | 2020-10-05: Mai Phước Thịnh
Task 11 | Form Quản lý mượn sách |  |  |  | 2020-10-05: Nguyễn Quốc Tuấn
Task 12 | Form Quản lý mức phạt |  |  |  | 2020-10-05: Nguyễn Quốc Khánh
Task 13 | Form thống kê tình trạng sách(còn,mượn,trễ hẹn) |  |  |  | 2020-10-05: Huỳnh Hoàng Huy
Task 14 | Form Quản lý thẻ đọc giả |  |  |  | 2020-10-05: Dương Khánh Ly
Task 15 | Form Quản lý trả sách |  |  |  | 2020-10-05: Nguyễn Thị Phương Thảo
Mã số sinh viên | Tên sinh viên
3118410148 | Huỳnh Hoàng Huy
3118410411 | Mai Phước Thịnh
3118410188 | Nguyễn Quốc Khánh
3118412034 | Dương Khánh Ly
3118410462 | Nguyễn Quốc Tuấn
3118412036 | Vũ Ngọc Minh
3118410407 | Nguyễn Minh Thiện
3118410397 | Nguyễn Thị Phương Thảo
3118410492 | Vũ Thị Hồng Xương

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
► Watch How This Gantt Chart Was Created
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.